## Task Tracker
AI-DA-AGENTS · Project Task Tracker
Retail Sales Analytics Chatbot ¦ Last updated: 06-Apr-2026
# | Category | Task Description | File(s) Changed | Status | Priority | Completed On | Notes
FOUNDATION
1 | Foundation | Replicate AIbot-Agents project into AI-DA-AGENTS | All src/ files | Done | High | Mar-2026 | Full project copy; confirmed identical structure in both repos
VISUALIZATION
2 | Visualization | Generate styled HTML table when user requests 'table' | src/visualization.py, app.py | Done | High | Mar-2026 | render_table_html() added; table label fixed in app.py
3 | Visualization | Fix pie chart always rendering as bar chart | src/visualization.py | Done | High | Mar-2026 | Added explicit_pie token check before semantic heuristics
4 | Visualization | Fix line chart when no date column present | src/visualization.py | Done | Medium | Mar-2026 | Falls back to label_index when date_index is None
5 | Visualization | Fix bar chart explicit detection | src/visualization.py | Done | Medium | Mar-2026 | Added explicit_bar / explicit_chart token layers
6 | Visualization | Replace keyword-driven auto-chart with data-driven rule | src/visualization.py | Done | High | Mar-2026 | Removed _COMPARE_KEYWORDS; chart only when row_count >= 2
7 | Visualization | Prevent HTML table creation for single-row scalar results | src/visualization.py | Done | Medium | Mar-2026 | Guard: if len(result.rows) >= _MIN_ROWS_FOR_AUTO_CHART
AGENT ENHANCEMENTS
8 | Agent Enhancements | Add Clarifier agent — ask follow-up for vague/open-ended questions | src/agents/clarifier.py (new), src/orchestrator.py | Done | High | Mar-2026 | Checks: time period (critical), dimension, metric. Reads history to avoid re-asking
9 | Agent Enhancements | Add Empty Result Handler — smart follow-up when SQL returns 0 rows | src/agents/empty_result_handler.py (new), src/orchestrator.py | Done | High | Apr-2026 | LLM acknowledges no data, states likely reason, asks ONE corrective question
10 | Agent Enhancements | Enhance Empty Result Handler to cite resolved entity attributes | src/agents/empty_result_handler.py, src/orchestrator.py | Done | Medium | 06-Apr-2026 | Passes self.last_entity_match; LLM says e.g. 'I searched SUBCLASS=JOGGERS but found nothing'
ENTITY RESOLUTION
11 | Entity Resolution | Add STATE entity resolver (embedding + fuzzy) | src/entity_search.py, src/orchestrator.py | Done | High | Mar-2026 | StateEntityResolver; threshold from settings
12 | Entity Resolution | Add CITY entity resolver | src/entity_search.py, src/orchestrator.py | Done | High | Mar-2026 | CityEntityResolver; shares cache with state resolver
13 | Entity Resolution | Add STORE_NAME entity resolver | src/entity_search.py, src/orchestrator.py | Done | High | Mar-2026 | StoreNameEntityResolver
14 | Entity Resolution | Add CATEGORY entity resolver with value embeddings | src/entity_search.py, src/orchestrator.py | Done | High | Mar-2026 | CategoryEntityResolver; threshold capped at 0.80
15 | Entity Resolution | Add SUBCLASS entity resolver (lower threshold for misspellings) | src/entity_search.py, src/orchestrator.py | Done | High | Apr-2026 | SubclassEntityResolver; threshold 0.78; catches 'Jogers' → JOGGERS
SQL INTELLIGENCE
16 | SQL Intelligence | Add brand vs category/subclass disambiguation rule for 'polo' | src/agents/sql_writer.py, business_context.json | Done | High | Mar-2026 | 'polo' alone → CATEGORY/SUBCLASS; 'USPA/US POLO' → BRAND
17 | SQL Intelligence | Add KPI definitions (ABV, ASP, ABS, ATV) to SQL writer | src/agents/sql_writer.py | Done | High | Mar-2026 | Full Unique Bills formula with INVOICETYPE CASE logic
18 | SQL Intelligence | Add growth KPI rule (MoM/YoY/WoW) to SQL writer | src/agents/sql_writer.py | Done | Medium | Mar-2026 | Returns current, previous, absolute change, % change
19 | SQL Intelligence | Add SQL debugger agent with auto-retry on DB error | src/agents/sql_debugger.py, src/orchestrator.py | Done | High | Mar-2026 | _execute_with_recovery(); retries = sql_debug_max_retries
20 | SQL Intelligence | Add semantic SQL cache (exact + cosine similarity) | src/sql_cache.py, src/orchestrator.py | Done | High | Mar-2026 | SQLite store; fingerprint on schema + business context; embedding lookup
BUG FIXES
21 | Bug Fixes | Fix 'polo' resolved as USPA brand instead of product category | src/agents/sql_writer.py, business_context.json | Done | High | Mar-2026 | Disambiguation rule + USPA note updated
22 | Bug Fixes | Fix chart label showing raw type instead of capitalised name | app.py | Done | Low | Mar-2026 | label = 'Table' if chart_type == 'table' else chart_type.capitalize()
23 | Bug Fixes | Fix single-row questions always creating an HTML table file | src/visualization.py | Done | Medium | Mar-2026 | Row count guard added to build_visual_output()

## Summary
Project Summary Dashboard
STATUS SUMMARY |  |  | TASKS BY CATEGORY
Status | Count | % of Total | Category | Tasks | Done
Done | 23 | 100% | Agent Enhancements | 3 | 3
TOTAL | 23 | 100% | Bug Fixes | 3 | 3
|  |  | Entity Resolution | 5 | 5
|  |  | Foundation | 1 | 1
|  |  | SQL Intelligence | 5 | 5
|  |  | Visualization | 6 | 6

## Change Log
Change Log
Date | Task # | Change Description | File(s) | Author | Status
Mar-2026 | 1 | Initial project replication from AIbot-Agents | All src/ | Dev | Done
Mar-2026 | 2 | Added render_table_html(); fixed app.py chart label | visualization.py, app.py | Dev | Done
Mar-2026 | 3 | Fixed pie chart detection (explicit token check) | visualization.py | Dev | Done
Mar-2026 | 4 | Fixed line chart fallback when no date column | visualization.py | Dev | Done
Mar-2026 | 5 | Added explicit bar chart detection | visualization.py | Dev | Done
Mar-2026 | 6 | Replaced keyword-driven chart logic with row-count rule | visualization.py | Dev | Done
Mar-2026 | 7 | Fixed single-row scalar results creating HTML table | visualization.py | Dev | Done
Mar-2026 | 8 | Added ClarifierAgent for vague questions | clarifier.py (new), orchestrator.py | Dev | Done
Mar-2026 | 11 | Added StateEntityResolver | entity_search.py, orchestrator.py | Dev | Done
Mar-2026 | 12 | Added CityEntityResolver | entity_search.py, orchestrator.py | Dev | Done
Mar-2026 | 13 | Added StoreNameEntityResolver | entity_search.py, orchestrator.py | Dev | Done
Mar-2026 | 14 | Added CategoryEntityResolver (threshold 0.80) | entity_search.py, orchestrator.py | Dev | Done
Mar-2026 | 16 | Added polo/USPA disambiguation rule | sql_writer.py, business_context.json | Dev | Done
Mar-2026 | 17 | Added KPI definitions to sql_writer instructions | sql_writer.py | Dev | Done
Mar-2026 | 18 | Added growth KPI (MoM/YoY/WoW) rule | sql_writer.py | Dev | Done
Mar-2026 | 19 | Added SQL debugger agent + auto-retry | sql_debugger.py, orchestrator.py | Dev | Done
Mar-2026 | 20 | Added semantic SQL cache (exact + cosine) | sql_cache.py, orchestrator.py | Dev | Done
Apr-2026 | 9 | Added EmptyResultHandler agent (0-row follow-up) | empty_result_handler.py, orchestrator.py | Dev | Done
Apr-2026 | 15 | Added SubclassEntityResolver (threshold 0.78) | entity_search.py, orchestrator.py | Dev | Done
06-Apr-2026 | 10 | Enhanced EmptyResultHandler with entity attribute context | empty_result_handler.py, orchestrator.py | Dev | Done